## MoSCoW Analysis
No. | Requirement | MoSCoW Category | Impact on Users / Stakeholders | Feasibility / Constraints | Justification
1 | Search books by title and author | Must-Have | High — core library function that helps users find books quickly and reduces manual work for librarians. | High feasibility — standard database search; relatively low cost and development effort. | Essential for the system's basic purpose and practical to implement within a limited project budget and timeline.
2 | Online book reservation system | Must-Have | High — lets users reserve unavailable or in-demand books and helps librarians manage demand. | Moderate to high feasibility — requires user accounts, availability tracking, and reservation rules, but uses standard application logic. | A key user service that can be delivered with common web-system components; prioritize a simple reservation workflow in the first release.
3 | Monthly reports on borrowed books for administrators | Should-Have | Moderate to high — supports planning, usage tracking, and administrative decisions, but is not needed for each borrowing transaction. | High feasibility — can be generated from borrowing and return records; requires report filters and export/display formatting. | Valuable for administration, but the core circulation system can operate before automated monthly reporting is added.
4 | Email notifications for overdue books | Should-Have | High — reminds users to return books and helps reduce overdue loans and librarian follow-up. | Moderate feasibility — requires an email service, scheduled checks, and valid user email addresses; may involve service configuration or costs. | Useful automation, but overdue status can initially be tracked manually or in the dashboard if time or email-service setup is constrained.
5 | QR code scanning for borrowing and returning books | Could-Have | Moderate — may speed up circulation and reduce manual entry, especially in busy libraries. | Moderate feasibility — requires QR generation, scanning hardware or camera access, and integration with loan records. | A convenience and efficiency improvement; standard barcode/manual lookup can support the initial release while QR workflows are deferred.
6 | User-friendly dashboard for librarians | Must-Have | High — librarians need a clear way to manage books, users, loans, returns, and reservations. | High feasibility — a basic dashboard can be built using standard web UI components; advanced analytics can be deferred. | Operationally essential for staff to use the system reliably. Keep the first version focused on core tasks.
7 | Allow users to review and rate books | Could-Have | Low to moderate — helps users discover books through community feedback but does not affect lending operations. | Moderate feasibility — needs review storage, rating logic, moderation, and possibly abuse prevention. | An optional engagement feature that can be added after core search, reservation, and circulation workflows are stable.
8 | Chatbot for user assistance | Could-Have | Moderate — can answer common questions and reduce repetitive enquiries, but is not essential for basic library operations. | Low to moderate feasibility under tight constraints — requires conversation design, reliable answers, testing, and possibly AI/API costs. | Useful enhancement, but cost and testing complexity make it suitable for a later phase; an FAQ page can cover common questions initially.
9 | Mobile app version of the system | Won't-Have (for this release) | Potentially high — offers convenient access on phones, but a responsive website can serve many of the same needs. | Low feasibility for a constrained first release — separate mobile development and testing increase time, cost, and maintenance. | Defer a separate native mobile app from the current release, not permanently; make the web system mobile-friendly and reconsider after launch.
10 | Multi-language support | Should-Have | Moderate to high in multilingual communities — improves accessibility and usability for users who prefer different languages. | Moderate feasibility — requires translation of interface text, language selection, and ongoing translation maintenance. | Important for inclusive access, but a single-language first release is feasible if time is limited; design the interface so additional languages can be added later.

## MoSCoW Guide
0 | 1
MoSCoW Category | Meaning used in this assessment
Must-Have | Essential for a usable first release; without it, core library operations are seriously affected.
Should-Have | Important and valuable, but the system can launch without it.
Could-Have | Desirable enhancement if time and resources permit.
Won't-Have (for this release) | Intentionally deferred from the current release; may be reconsidered in a future version.
Planning assumption | This categorization assumes a limited first-release timeline, budget, and development team. Priorities may change with stakeholder input.